## Sheet1
Features | Not Started | In Progress | Done |  | Yesterday | Today | Impediment
Hangman |  |  | x | Hannah | Wrote code for outputting word after guesses in VS code then converted it to Unreal and pushed it to repository | Retested code for Hangman feature after changing format. Helped Josh with the time feature | issues with testing and formatting but finished
Level Design |  | x |  | Liam | Finished playable area | Expand forest | none
Time |  | x |  | Josh | wrote code for time in one function | wrote code for passing the timer through functions | get timer to pass between funcitons without resetting
Score |  |  | x | Justen | implemented score feature | assist Josh with time implementation | none